## Slide 1: LARC WEBINAR
How easy is it to do a QI project?
Nicholas Makombe

## Slide 2: Epworth and Overspill
IHI COURSES

## Slide 3: Brief description of the HCW
Total of 9 participants were supposed to take IHI courses
4 were from Overspill,5 were from Epworth
2 managed to register and complete one course
All HCW were using personal gadgets

## Slide 4: GAP
Two out of nine health care workers have started the mandatory 7 IHI courses

## Slide 5: AIM
To have all 9 health care workers register and at least complete 1 out of the the 7 mandatory IHI courses by the 7th of August 2020

## Slide 6: METRIC
Number of health care workers at Epworth and Overspill who registered and started the IHI courses by 07 August 2020

## Slide 7: MEASURE
Baseline Measure
Data source
Sample size
Number of health care workers who have started the IHI course
IHI Database
9 health care workers (Epworth and Overspill)

## Slide 8: FISHBONE ANALYSIS
78 % of HCW not yet started the mandatory 7 IHI courses
PEOPLE
ENVIRONMENT
PROCESS
Materials/Equipment
No laptops
No data
Failure to register on IHI
Lack of information on how to register.
Poor internet connection

## Slide 9: INTERVENTION
Japhet and Fortunate to assist with registration of the health care worker emails on the IHI website virtually.

## Slide 10: PDSA CYCLE 1
PLAN
Japhet to use team viewer to assist the participants to register for the IHI courses
ACT
Abandon using team viewer. Japhet to open accounts for the rest of the participants remotely and send the details for them to use on their smart phones
STUDY
Only the
DEC at Epworth had access to a computer with team viewer the other participants had smart phones. Only 1 participant had an account opened.
DO
Japhet called the DEC for Epworth and asked him to download team viewer on his computer and assisted him to open an account on the IHI website and register for the courses

## Slide 11: PDSA CYCLE 2
PLAN
Japhet to open email accounts for the remaining 6 participants
ACT
Implement the strategy for any other participants having log in challenges
STUDY
All the participants are now registered for the IHI courses after Japhet’s intervention
DO
Japhet opened the email accounts for the remaining 6 participants and registered them for the IHI courses

## Slide 12: Q&A
1) Did this take you a lot of time?
  It doesn’t take a lot of time to get the information as per phone from the participants of the project. There is need for airtime to call the participants for clarification of issues
2) How does QI “save you time”?
  By making sure that you use strategies that work and abandon the ones that do not work
3) How important is data in QI?
  Shows where there is an improvement in a project and whether the change ideas are working or not.

## Slide 13: Thank you